## How to use
Binggio 0.1 user acceptance test
What this is | 78 end-to-end cases covering install, the app, the sample bank, adding data, discovery, onboarding, review, data changes, asking, safety, performance and the screens. Release when every P1 case passes.
The agent | python uat\run_uat.py runs every case it can on a fresh simulated machine and fills in "Agent result" and "Agent finding" in a copy of this workbook (uat\reports\UAT_results_<time>.xlsx). Add --with-model for questions in your own words, --sqlserver "host=localhost;database=master;windows" for SQL Server.
Agent result | PASS: checked against independent counts or exact values. FAIL: clearly wrong. AMBIGUOUS: the agent cannot decide; you decide. NOT RUN: needs a server, Playwright or a model key on this PC.
What you fill in | Only the yellow columns: Your result (choose from the list), Tester, Date, Notes. Give every AMBIGUOUS case a verdict, and re-test FAIL cases after the fix.
Your result | PASS, FAIL, BLOCKED (cannot be tested yet) or N/A (does not apply to this release).
Example row | Your result: FAIL · Tester: Ashish · Date: 30-Oct-2026 · Notes: Refresh listed "accounts, loans" as changed but only accounts changed.
Release rule | All P1 cases PASS (by the agent or by you), no FAIL left open, every AMBIGUOUS case decided. The Summary tab counts these.
Columns to fill in | Yellow
Filled by the agent | Grey

## UAT cases
ID | Area | Priority | Test | Steps | Expected result | How it is run | How the agent decides | Agent hands it to you when | Agent result | Agent finding | Your result | Tester | Date | Notes
INS-01 | Install | P1 | Install from the built package into a clean Python | 1. Build the wheel from a clean copy of the source 2. Create a new virtual environment 3. pip install the wheel | Install succeeds with no extra dependencies | Agent | pip exit code 0; binggio has no required dependencies | -
INS-02 | Install | P1 | Installed files are exactly the source | Compare every installed file with the source tree | Every file identical; none missing (UI page and sample bank included) | Agent | byte comparison of all files | -
INS-03 | Install | P1 | binggio --version and --help | Run binggio --version, then binggio --help | Version 0.1.0 printed; help lists ui, onboard, ask | Agent | exit code and text | -
INS-04 | Install | P1 | python -m binggio works when the command is not on PATH | Run python -m binggio --version | Same output as binggio --version | Agent | exit code and text | -
INS-05 | Install | P2 | Excel extra installs | pip install openpyxl into the environment (binggio[excel]) | Excel support available | Agent | import works after install | install fails because there is no internet (cannot tell a packaging fault from a network fault)
LIC-01 | Install | P1 | Licence is the official AGPL-3.0 text and the package declares it | Check LICENSE in the source and the installed package metadata | LICENSE is the unchanged GNU AGPL v3 text; metadata says AGPL-3.0-or-later; source files carry the SPDX header | Agent | file heading, version line and length; metadata; headers on every source file | -
INS-06 | Install | P1 | Commands outside a workspace explain what to do | In an empty folder run binggio status | Clear message "No Binggio workspace found ... Run: binggio init"; exit code 2, no traceback | Agent | exit code 2 and message; no "Traceback" in output | -
APP-01 | App | P1 | binggio ui starts and prints its address | Run binggio ui --no-browser in a folder that is not a workspace | Address http://127.0.0.1:<port>/ printed within 10 s; start screen served | Agent | address printed; page contains the app | starts but takes 10-30 s
APP-02 | App | P1 | API refuses requests without the session token | Call the API with no token and a wrong token | HTTP 403 both times | Agent | status codes | -
APP-03 | App | P1 | API refuses another host name (DNS rebinding) | Call the API with Host: evil.example | HTTP 403 | Agent | status code | -
APP-04 | App | P1 | Start screen: create the sample bank | Choose a folder, name it, click Create the sample bank | Sample bank created; app opens on Ask | Agent | workspace created; status shows 63 answerable tables | -
APP-05 | App | P2 | Start screen: open an existing workspace and the recent list | Open a workspace by folder; restart the app; check Recent | Workspace opens; it appears in Recent after restart | Agent | open succeeds; recent list contains it | -
APP-06 | App | P1 | Opening a folder that is not a workspace is explained | Open /not/a/workspace | Clear error, app stays usable | Agent | HTTP 400 with a message containing "workspace" | -
DEMO-01 | Sample bank | P1 | Overview numbers | Open Overview on the sample bank | 10 sources, 85 tables, 63 ready for questions, 429 approvals current, 0 changed | Agent | exact numbers | -
DEMO-02 | Sample bank | P1 | No POC names or personal names visible | Look at sources, concepts and the activity list | No "Phase1", "POC", "decision round" or personal names | Agent | text search of every listed name, description and actor | -
DEMO-03 | Sample bank | P1 | Ten sample questions give the verified answers | Click each sample question on Ask | Each answer matches the verified answer (tests/golden) | Agent | rows compared with the verified answers | -
DEMO-04 | Sample bank | P1 | Follow-up questions use the previous answer | Run the 3-step sample (top 10 loans -> which are delinquent -> their customers) | 10 loans, then 9, then the 9 customers | Agent | row counts and ids | -
DEMO-05 | Sample bank | P1 | Every answer shows where it came from | Open an answer's details | Source tables, business terms with meanings, as-of date, steps in plain words, the query | Agent | fields present and non-empty | -
DEMO-06 | Sample bank | P1 | Asking in your own words without a key is explained | Type a question with no model key set | Not answered: needs a model key, with a link to Settings | Agent | refusal code MODEL_NOT_CONFIGURED | -
DEMO-07 | Sample bank | P2 | Overview opens quickly | Open Overview on the sample bank | Under 2 seconds | Agent | timed API call | 2-5 seconds (acceptable on a slow PC?)
SRC-01 | Data sources | P1 | Add a messy CSV export | Data sources -> CSV folder -> Browse to the export -> Add and profile | 4 tables added, profiled, relationships found; no errors | Agent | job finishes; 4 tables; 0 profile failures | -
SRC-02 | Data sources | P1 | Folder picker lists folders and counts CSV files | Browse to the export folder | Shows the folder and "4 CSV files in this folder" | Agent | API listing | -
SRC-03 | Data sources | P1 | Add an Excel workbook with title rows above the header | Excel workbook -> choose the file -> Add | Header found on row 3 for every sheet; 4 tables | Agent | notes and table count | -
SRC-04 | Data sources | P1 | Old .xls is refused with advice | Add an .xls file | Refused: "save as .xlsx"; nothing added | Agent | job fails with that message; source count unchanged | -
SRC-05 | Data sources | P1 | Add a SQLite database | SQLite file -> choose the .db -> Add | 4 tables; declared primary keys kept | Agent | table count; declared keys on the profile | -
SRC-06 | Data sources | P1 | Test connection lists tables before copying | SQLite: Test connection and list tables | The 4 table names listed; nothing copied yet | Agent | list returned; source count unchanged | -
SRC-07 | Data sources | P2 | Broken files are reported, not fatal | Add a folder with an empty CSV, a CSV with duplicate headers and one good CSV | Good table profiled; the two broken ones reported | Agent | job done; 2 profile failures reported | -
SRC-08 | Data sources | P1 | Original files are never changed | Hash the CSV, Excel and SQLite files before and after adding and refreshing | Hashes identical | Agent | sha256 before and after | -
SRC-09 | Data sources | P1 | Refresh after the source changes | Change one row in the SQLite file -> Refresh | Only the changed table reported as changed | Agent | changed_tables == [accounts] | -
SRC-10 | Data sources | P1 | SQL Server: test connection, add, refresh | SQL Server tab -> host, database, Windows sign-in -> Test -> Add | Tables listed and copied read-only; declared keys kept; answers same as CSV | Agent + server | with --sqlserver: list, add and answer checks | connects but some tables are skipped or keys missing (rights?)
SRC-11 | Data sources | P2 | Oracle: test connection and add | Oracle tab -> host, service, user, password -> Test -> Add | Tables listed and copied read-only | Agent + server | with --oracle | -
SRC-12 | Data sources | P2 | PostgreSQL: test connection and add | PostgreSQL tab -> details -> Test -> Add | Tables listed and copied read-only | Agent + server | with --postgres | -
SRC-13 | Data sources | P2 | A missing database driver is explained | Open the SQL Server tab without pymssql installed | Message: pip install binggio[sqlserver]; Add is disabled | Agent | state reports driver missing; API error text | -
DISC-01 | Discovery | P1 | Own keys suggested correctly | After adding the CSV export, look at suggested roles | customers.customer_id, accounts.account_id, loans.loan_id, repayments.repayment_id suggested as primary keys | Agent | exact set | -
DISC-02 | Discovery | P1 | Links found, including a column not named *_id | Look at candidate relationships | accounts -> customers, repayments -> loans, loans.cust_ref -> customers | Agent | required links present | -
DISC-03 | Discovery | P1 | No noise links | Look at candidate relationships for the CSV export | No links other than the 3 real ones | Agent | extra links counted | an extra link scores 0.85-0.90 (pre-ticked for approval, could be wrong)
DISC-04 | Discovery | P1 | Collections source (10 tables): links and keys | Add the 10-table collections fixture to a workspace with the CSV bank | The 11 verified links found; anything else scores under 0.85 and is left for a person; 10 of 10 own keys right | Agent | compared with the verified lists | a link outside the verified list scores 0.85-0.90 (it would be pre-ticked for approval)
DISC-05 | Discovery | P1 | Messy values match: " c0007 ", "1,234.50", BOM, semicolons | Answers on the messy CSV export | Answers equal the independent counts | Agent | compared with the independent counts | -
ONB-01 | Onboarding | P1 | Impact report classifies each table | Onboard the CSV export | Each table classified (new entity / lookup list / records) with a reason | Agent | every table has a kind and a reason | -
ONB-02 | Onboarding | P1 | A copy of an existing table is flagged as a duplicate and left out | Onboard the collections source into the sample bank (borrower_profile is a copy of customer_master) | Classified Duplicate; its columns are not offered for approval | Agent | kind == duplicate; table absent from step 1 | -
ONB-03 | Onboarding | P1 | Approving the suggestions | Onboard -> Approve selected (with your name) | 21 roles, 3 links, 4 concepts approved; no errors | Agent | counts | -
ONB-04 | Onboarding | P1 | Words for a coded value become a business term | Give "closed account" for accounts.status = CLOSED | Term approved; a question using it filters status = CLOSED | Agent | term approved; plan with the term returns the CLOSED accounts | -
ONB-05 | Onboarding | P1 | Weak links are left for a person | Onboard the collections source (cust_no -> customer_kyc_profiles scores about 0.77) | That link is unticked and stays waiting | Agent | suggested == false for scores < 0.85; still pending after apply | -
ONB-06 | Onboarding | P1 | Decisions need a name | Approve without entering a name | Asked for a name; nothing recorded without one | Agent | HTTP 400; no new events | -
REV-01 | Review | P1 | Approve, revoke, reopen and re-approve a column role | Review -> Column roles -> tick one -> each action in turn | Status moves Approved -> Revoked -> Waiting -> Approved; each recorded | Agent | status after each action; history has 4 entries | -
REV-02 | Review | P1 | Change a role before approving | Pick a different role in the list, then Approve | The chosen role is stored | Agent | approved role equals the chosen one | -
REV-03 | Review | P1 | Same cycle for a relationship, with a kind | Review -> Relationships -> revoke, reopen, approve as Many to one | Recorded with the chosen kind | Agent | status and cardinality | -
REV-04 | Review | P1 | Same cycle for a business term and a concept | Review -> Business terms / concepts -> Revoke, Reopen, Approve | Each status change recorded | Agent | status after each action | -
REV-05 | Review | P1 | Bulk approve | Tick 5 waiting roles -> Approve | 5 recorded | Agent | done == 5 | -
REV-06 | Review | P1 | Impossible actions are refused per item | Reopen an item that is approved | That item not changed, with the reason; others unaffected | Agent | done == 0 and an error per item | -
REV-07 | Review | P1 | Revoking a link stops answers that need it | Revoke accounts -> customers, ask open balance by segment | Not answered (the link is not approved) | Agent | refused | answered through another approved path (is that path right?)
REV-08 | Review | P1 | Activity shows every decision with name and note | Open Activity | All decisions from this run, newest first, with names and notes | Agent | events from this run present with actor and note | -
CHG-01 | Data changes | P1 | Changed data makes its approvals stale | Change the source, refresh, profile | Only the changed table's approvals show Data changed | Agent | stale count > 0 and only for that table | -
CHG-02 | Data changes | P1 | Stale approvals are not used for answers | Ask a question needing the changed table | Not answered, with the reason | Agent | refused | -
CHG-03 | Data changes | P1 | Re-approving restores answers | Approve the stale items again, ask again | Answered, using the new data | Agent | answer equals the count on the new data | -
CHG-04 | Data changes | P1 | Touching files without changing them keeps approvals | Change file times only | Nothing becomes stale | Agent | stale == 0 | -
ASK-01 | Ask | P1 | Answers on your own data equal independent counts | Ask the 7 checked questions on the CSV export | All 7 equal the independent counts | Agent | compared with the independent counts | -
ASK-02 | Ask | P1 | CSV, Excel and SQLite give identical answers | Ask the same 7 on each source | Identical | Agent | equality | -
ASK-03 | Ask | P1 | Long lists show 200 rows and the total | Ask for all loans of a 300,000-row table | 200 rows shown, total given | Agent | rows == 200 and row_count == total | -
ASK-04 | Ask | P1 | Nothing approved: the message says what to do | Ask in a new workspace with nothing approved | Not answered: approve column roles and relationships first | Agent | refusal code NOTHING_APPROVED | -
ASK-05 | Ask | P1 | Follow-up without a previous answer is refused | Start a new conversation and ask "which of these ..." | Not answered: no previous result | Agent | refusal code COHORT_NOT_AVAILABLE | -
NL-01 | Ask (own words) | P1 | Clear questions on the sample bank | Ask 8 clearly worded questions with a model key | Each answer equals the verified answer | Agent + model | rows compared with the verified answers | the right rows plus extra rows or columns, or refused with a reason (wording or engine?)
NL-02 | Ask (own words) | P1 | Badly worded questions (typos, shorthand, no punctuation) | Ask 6 sloppy versions of verified questions | Same answers as the clean versions | Agent + model | rows compared with the verified answers | refused, or partly right
NL-03 | Ask (own words) | P1 | Questions with two possible meanings are not guessed | Ask "show revenue", "KYC status of customers" | Not answered; asks which meaning | Agent + model | refused as ambiguous | answered (which meaning did it choose, and is that acceptable?)
NL-04 | Ask (own words) | P1 | Questions the data cannot answer are refused | Ask about data that does not exist (credit card limits, employee salaries) | Not answered, with the reason | Agent + model | refused | answered from a column that might be related
NL-05 | Ask (own words) | P1 | The same question twice gives the same answer | Ask one question twice in new conversations | Identical rows | Agent + model | equality | different rows
NL-06 | Ask (own words) | P1 | Follow-ups in your own words | "Top 10 loans by outstanding balance" then "which of these are delinquent" | 10 then 9 loans | Agent + model | ids | second step refused
MCP-01 | AI agents | P1 | An agent gets governed answers through binggio mcp | Start the installed binggio mcp on the sample bank; as an MCP client: initialize, list tools, describe, run a plan, try an invented column, propose a term | Verified answer with sources; invented column refused; proposal saved as a draft; no tool can approve | Agent | protocol replies, rows compared with the verified answer, registry state | -
SAFE-01 | Safety | P1 | A model key typed in the app is not written to disk | Settings -> paste a key -> use it; search the workspace and home folder | Key not found in any file | Agent | byte search of every file | -
SAFE-02 | Safety | P1 | A database password typed in the app is not written to disk | Add a database with a password; search the workspace | Password not found in any file | Agent | byte search of every file | -
SAFE-03 | Safety | P1 | Moving the workspace keeps every approval | Copy the workspace folder elsewhere and open it | Same approvals, same answers | Agent | status and answers equal | -
SAFE-04 | Safety | P1 | Uninstall leaves workspaces alone | pip uninstall binggio | Command gone; workspaces intact | Agent | files present | -
PERF-01 | Performance | P1 | 300,000-row table end to end | Add, profile, discover, onboard, ask a total by segment | Exact totals; each step under 30 s | Agent | totals exact; timings | a step takes 30-90 s
UI-01 | Screens | P1 | Every screen opens without errors | Open all 11 screens | No script errors; each shows content | Agent + browser | page errors and content | -
UI-02 | Screens | P2 | Works at phone width | Open Review at 390 px wide | No sideways scrolling of the page | Agent + browser | page width equals window width | -
UI-03 | Screens | P1 | Start screen to first answer by clicking | Create a workspace, add the CSV export, onboard, ask a sample-bank question | Completes by clicking only | Agent + browser | each step reaches its expected screen | -
UI-04 | Screens | P2 | Download an answer as CSV | Ask a sample question -> Download CSV | A CSV with the same rows | Agent + browser | downloaded rows equal the answer | -
UI-05 | Screens | P2 | Keyboard: the question box and dialogs | Press Enter to ask; Esc closes a dialog | Both work | Agent + browser | answer appears; dialog closes | -

## Summary
Summary
Counts update as results are entered. "Decided" = your result if given, otherwise the agent's PASS or FAIL.
Area | Cases | P1 | Agent PASS | Agent FAIL | Ambiguous | Not run | Your PASS | Your FAIL
Install
App
Sample bank
Data sources
Discovery
Onboarding
Review
Data changes
Ask
Ask (own words)
AI agents
Safety
Performance
Screens
Total
Release check
P1 cases decided PASS
P1 cases in total
Open failures
Ambiguous without your verdict
Ready to release